## Slide 1
Common Platform – Implementation Update
12/11/2020

## Slide 2: Early Adopter rollout
Preparations are underway to continue rolling out Common Platform to the remaining Early Adopter sites (pairs of Crown and Magistrates’ courts) subject the approval of the programme board and the SPJ. Learnings from Derby are being taken forward in planning and preparation activities for the next early adopter courts. Local Implementation Teams have been established to engage the Judiciary and all partner agencies involved.
The current view on working towards go live dates (which are all subject to approval) are:
South West Bristol Magistrates and Crown Court – during November
North East North Tyneside, Mid & South East Northumberland and Berwick Upon Tweed Magistrates Courts and Newcastle Combined Crown Court - Nov/ Dec
South East Guilford and Staines Magistrates Court and Guildford Crown Court-likely to be January 2021
London Croydon Magistrates and Crown Court -likely to be February 2021
North West Warrington Magistrates Court and Chester Crown Court -likely to be early 2021
Wales Llanelli Magistrates Court and Swansea Crown court -likely to be early 2021

## Slide 3: Defence awareness
We have held 11 sessions for defence practitioners and had 160 attendees.
Further awareness sessions will be held on the following dates via Microsoft Teams (the links will be live at the event times shown and others will be added in due course) - please feel free to forward them:
        18 Nov at 5-6pm
        24 Nov at 5-6pm
        03 Dec at 5-6pm
        10 Dec at 5-6pm
        17 Dec at 5-6pm
        13 Jan at 5-6pm
        20 Jan at 5-6pm
        26 Jan at 5-6pm
        04 Feb at 5-6pm
We held a Defence Webinar on 15 October introducing Common Platform - the recording is here: https://www.gov.uk/guidance/hmcts-online-event-15-oct-2020-introducing-the-common-platform

## Slide 4: Defence learning
Defence learning guide is iterative as we take on board feedback - we are at version 7.
Shortly, the latest version of the Defence learning guide will be placed on the GOV.UK pages alongside the registration spreadsheet: https://www.gov.uk/guidance/hmcts-common-platform-account-registration-for-defence-professionals
We are also producing a short video which will be a useful introduction for defence practitioners and will show the process of Common Platform account registration and security set-up.

## Slide 5: Defence onboarding
 | Duty solicitors | Defence community
Derby | 100% | 60%
Bristol | 54% | 17%
Companies contacted via direct email – Derby, Bristol and South East | Companies provided a response – includes multi region from webinar response | Total users identified (at various stages on being processed)
157 | 83 | 964
To register for an account please use the following link:
https://www.gov.uk/guidance/hmcts-common-platform-account-registration-for-defence-professionals